## About the table
Agency commitments table - current as at 16 March 2026
Monitored agencies are required to formally respond to our reports. They have 20 working days to respond to our Experiences of Care in Aotearoa and Outcomes for Tamariki Māori reports, and 35 days to respond to our focussed in-depth reviews. Once we receive these formal responses we have 10 working days to publish our report, alongside the responses we receive. These responses often include commitments from agencies to do things that will address issues raised in our reports. We keep track of these commitments and what progress has been made. We assess progress based on the completion dates originally provided by agencies. This table includes a list of agency commitments that: • clearly relate to findings we have made in one or more of our reports • are specific and detailed • are still being progressed by an agency, or have been recently completed. The table does not include every finding we have made – only those where an agency has made a clear commitment in response. We follow up on other findings we made which are not included in this commitments table, through our future published reports. The table also does not include commitments arising from our two Towards a stronger safety net to prevent abuse of children reports, as we follow up on these separately through our published reports.
Abbreviations explained:
EoCA | Experiences of Care in Aotearoa Report
NCS | National Care Standards made under the Oranga Tamariki (National Care Standards and Related Matters) Regulations 2018
OfM | Outcomes for tamariki and ranagathi Māori and their whānau report

## Agency commitments
Report | Agency | Finding made | NCS Part/relevant legislation | Year(s) made | What agency intends to do in response to finding | Completion due date | Update (complete, progressing - on track, Progressing - off-track, not progressing) | Narrative response (to progress update) | Date of update | Aroturuki Tamariki assessment progress of action
EoCA | Oranga Tamariki | Caregivers need more support. | Part Three | 2020/21, 2021/22 | Reform the system of financial assistance and support for caregivers. | June 2029 (part of a four-year work programme commencing July 2025). | Progressing - on track | Oranga Tamariki has established a 4-year Integrated Safe Care Response Programme, in part to deliver on the Budget 25 initiative ‘Recognising and Responding to Abuse in Care’. Changes to financial support for caregivers is one part of this broader work programme. | 23/02/2026
EoCA | Oranga Tamariki | For social workers to successfully perform their role they need to be able to spend more time with tamariki, rangatahi, whānau, caregivers and communities. | Overarching | 2021/22, 2022/23 | Development of an organisational demand and allocation model to be implemented in 2022/23 financial year. | Completion date for development of the youth justice social work tool is unknown. Care and protection social work tool has been completed. | Progressing - on track | Oranga Tamariki started using a new strategic workforce analysis reporting tool in the last three months of 2025. The tool brings together demand, workforce, workload and workflow metrics. The tool is used by site and regional leadership to support oversight and decision-making around capacity of the social worker workforce. The tool is currently most focussed on care and protection social work. A similar tool is being developed for youth justice social work. A prototype modelling approach has also been developed to better understand the impact of changes in demand or practice settings on care and protection social work capacity, to inform future workforce planning. | 2026-02-23
|  |  | Overarching | 2021/22, 2022/23 | Office of the Chief Social Worker will focus on better understanding social worker capacity, caseload complexity and workload management. | Completed | Complete | Oranga Tamariki has undertaken work to understand case complexity and to develop a predictive model to predict case complexity. These two reports have been published on the Oranga Tamariki website https://www.orangatamariki.govt.nz/about-us/research/our-research/measuring-case-complexity/ | 2026-02-23
EoCA | Oranga Tamariki | Tamariki and rangatahi are still not receiving the minimum standard of care required by the National Care Standards Regulations. | Overarching | 2023/24, 2024/25 | Implementation Plan developed and being implemented which is focussed on the following: Social worker visits to tamariki, Reducing placements with unapproved caregivers, Allocating cases on time, Finding and returning missing tamariki to care, Completing safety assessments for critical and very urgent Reports of Concern on time, Improving complaint management, Improving support for caregivers. | Ongoing - plan in place until at least 1 July 2026. | Progressing - on track | In April 2025 Oranga Tamariki started delivering against a National Care Standards Action Plan. This plan is intended to improve the agency's compliance with the NCS Regulations. This is different to the 'Implementation Plan' that Oranga Tamariki originally identified in response to our findings. There are 10 areas of focus in the plan. As identified in the Oranga Tamariki Annual Report for 2024/25 and in Appendix B of the Experiences of Care in Aotearoa 2024/25 report, these focus areas relate to (1) visits to children in return home placements; (2) visits to children in care; (3) transition to adulthood planning in All About Me Plans; (4) children having current All About Me Plans; (5) All About Me Plans having actions to support family, whānau, hapu, iwi, marae and family group connections; (6) caregiver visits; (7) caregiver and placement approvals; (8) assessment reports for children in care; (9) enrolment and engagement with GPs/PHOs for children in care; (10) reducing peer-to-peer harm in residences. Oranga Tamariki monitors its performance against this plan periodically. Across the 10 areas in the plan, there have been gradual improvements in most areas since the plan began in April 2025. | 23/02/2026
EoCA | Oranga Tamariki | Social workers are not always able to work effectively, and some things are getting in the way of social workers doing social work. | Overarching | 2023/24, 2024/25 | The Oranga Tamariki Frontline Technology Systems Upgrade (FTSU) will replace old technology, including the CYRAS case management system (CYRAS). FTSU will simplify information recording and reduce the need to duplicate recording information across systems, freeing up social worker time. | Delivery timeframes for FTSU are not yet confirmed (it will be a multi-year project delivered in three tranches). Release of the new All About Me Tool is scheduled for 3 May 2026. | Progressing - on track | Oranga Tamariki received a $68.5m funding boost over five financial years through Budget 2025, to invest in frontline technology systems, increasing the amount of time social workers can spend with children and whānau. The Frontline Technology Systems Upgrade will replace legacy systems that are no longer fit for purpose, including the existing case management system social workers use every day, which is now more than 20 years old. The new system will increase the amount of time social workers have to engage with children, young people, whānau, victims, caregivers and partners by: • reducing duplication • making it easier to search, find and use information • improved ability to use, see and manage notifications clearly • enabling the reuse of information already captured to reduce double keying • visibility across tamariki/rangatahi journey through the system • access to information outside the office • ability to collaborate with other frontline kaimahi easily • easily and securely communicate with agencies, whānau, partners, tamariki and rangatahi. Oranga Tamariki is also developing a new tool to record the All About Me Plan. The new tool will make it easier to record important information. It will be able to be worked on alongside tamariki and rangatahi in a more collaborative way. Kaimahi will be able to input information and re-use information in other documents to minimise duplication of effort. In the interim, before completion of FTSU, Oranga Tamariki is making other technology improvements for frontline kaimahi. This includes digitising the report of concern form which will automate some administrative tasks and reduce follow-ups. Oranga Tamariki is also piloting an AI tool to enable social workers to access practice centre resources more easily. | 23/02/2026
[5 empty] | Continue to implement and embed the Practice Approach – which should enable social workers to better understand and meet the needs of tamariki and whānau and to work in new ways. | Completed (Practice Approach programme). Embedding will occur through business-as-usual activities. | Complete | Oranga Tamariki has continued to implement and embed the Practice Approach, with significant progress made through the completion of the first two Learning Cycles and delivery of the final learning cycle - Learning Cycle 3 (LC3) in 2024. Through the final learning cycle, Oranga Tamariki developed new practice models and tools, refreshed practice policy and guidance, and supported location based learning, trialling and validating new approaches. During 2025, the following tools and resources were rolled out: • Redeveloped Practice Models – Te Toka Tūmoana, the practice model for working with tamariki and whānau Māori, and Va'aifetū, the practice model for working with Pacific children and families. These practice models will deepen kaimahi understanding about the situations Oranga Tamariki is working with and be guided in the changes needed to improve the oranga / wellbeing of the tamariki and children. • Oranga Framed Practice Prompts – this tool helps social workers explore the safety of children using a holistic framework including physical, emotional, mental, whānau, spiritual, and environmental wellbeing. • Organising My Practice Resource – this is a tool social workers are using to plan their work. This tool helps social workers think about what information they need to gather, who they need to engage with and what knowledge (legislation, policy etc) they might need to draw from. It also helps them think through any blind spots and areas where they might need further advice and supports. • Tiaki Oranga – this is a new tool used to support understanding about the immediate safety of a child whilst further assessment and planning occur. It is used to inform safety plans for children and is a more comprehensive approach to establishing safety than the previous safety and risk screen. • New Assessment Approach and Report – a new approach and report template that has replaced Tuituia. The new assessment approach is 80 percent in building and deepening understanding, including through use of the aforementioned practice tools. The remaining 20 percent is the articulation of the social work reasoning in an Assessment Report. | 23/02/2026
EoCA | Oranga Tamariki | Tamariki and rangatahi in care are not prioritised for government services and funding does not follow the child. | Part Two | 2023/24, 2024/25 | In relation to health, agencies will be enhancing visibility of children in care in the health system. | Delivery timeframes are not yet confirmed - Detailed project plans with timeframes are currently being worked through with Health New Zealand. | Progressing - on track | Making care status visible to health practitioners Agencies have proposed to make care status visible to health practitioners (who have appropriate user permissions) by placing a flag showing care status on a child’s National Health Index (NHI) number. In December 2025, Ministers agreed to this approach and funding was identified to support this work. With this approval and funding secured, agencies are now able to allocate resource accordingly and begin work to build the technical solution. Guidance for health practitioners will also be developed to support them to tailor their practice and respond to the unique needs of children and young people in care. Information sharing agreement between Oranga Tamariki and Health New Zealand Agencies are scoping the work required to develop the information and data sharing agreements that will enable Oranga Tamariki to share care status information with Health New Zealand and receive essential health service information about children and young people in care. The latter will support with monitoring and reporting on compliance with the National Care Standards. For example, information shared may include data on access to a General Practitioner, dental checks, immunisation status, and Before School Checks. It is expected that operational data sharing will be rolled out in phases as the agreements are developed. | 23/02/2026
EoCA | Oranga Tamariki | More tamariki and rangatahi are being abused in care. | Part Five | 2023/24 | Focusing on quality practice by rolling out a new Practice Framework to support staff with improved practice. | Oranga Tamariki- operated residences and community homes Timeline for full implementation of the new residences and community homes Model of Care is not currently confirmed. A pilot in one residence is planned to occur March-August 2026. Other care settings June 2029 (part of a four-year work programme commencing July 2025). | Progressing - on track | Oranga Tamariki-operated residences and community homes A Model of Care for Oranga Tamariki-operated secure residences and community homes has been developed and was approved on 21 January 2026. Implementation planning is underway. The Model of Care strengthens the safety and rights of tamariki and rangatahi by embedding rights based, trauma informed, and relational practice across the care journey, creating environments where tamariki feel safe, heard, and supported. The Model of Care is intended to prevent abuse in care by: • Providing consistent, predictable, and least restrictive care, supporting emotional regulation and physical and psychological safety through proactive, therapeutic, and culturally responsive approaches. • Using the three pou to ensure intentional and safe placements: 1. Whakatau – stabilising risk and behaviours. 2. Whakaoranga – restoring wellbeing. 3. Whakawhanaungatanga – building capacity for return to whānau and community. • Strengthening kaimahi capability through multidisciplinary practice, clear guidance, high quality supervision, and the skills required to respond safely and confidently. • Setting clear practice expectations and accountability, supported by strong leadership, risk management, ongoing training, and assurance processes to identify concerns early. • Promoting trauma informed responses to complex needs, focusing on de-escalation, avoiding harmful or punitive responses, and ensuring least restrictive practices are used only when necessary and for the shortest time. Other care settings Practice improvements to prevent abuse in care settings that are not residences or community homes will be part of the broader Integrated Safe Care Response Programme that Oranga Tamariki has established. This is a four-year work programme. | 23/02/2026
[5 empty] | Residences – individualised and targeted action plans for each facility with a focus on reducing harm and improving the environments. | No completion data provided as actions plans for residences are now an ongoing process embedded into business as usual activity. | Progressing - on track | Individual action plans are in place for the Oranga Tamariki-operated residences. Residence managers are accountable for delivery of work on their respective action plan. They are living documents that encapsulate significant pieces of work underway at each site. The relevant Manager Residential Care is accountable to the Deputy Chief Executive for delivery of all plans across their span their responsibility.
[5 empty] | Residences – focusing on improving practice for frontline kaimahi through skills training and professional development. | Professionalising the Residential Workforce Programme This is a four-year work programme commencing in Financial Year 2025/26 | Progressing - on track | Te Waharoa, the induction programme for new staff, is reviewed at regular intervals. Iterative enhancements to the programme occurred throughout 2025, and this will continue in 2026, including through the Professionalisation of the Residential Care Workforce initiative. In early 2026, the programme is being revised to extend the initial three-week training period to four weeks. In Budget 2025, funding was allocated to the work programme, Professionalising the Residential Workforce. This programme is underway. To date work has been completed to develop the implementation plan, project management plan and to undertake early procurement activities. The programme will support strategic workforce development for youth justice residences. Key changes will include: • A Model of Care-aligned approach integrating learning, operational leadership, deployment and practice. • Defined learning and qualification pathways, including revised induction, core learning, continuous development, a bespoke NZQA‑recognised micro‑credential, and supported external qualifications (e.g., advanced youth work, social work). • New specialist and practice leadership roles (Practice Leads, Training Leads, Advanced Practitioner Teams) to strengthen the support system for consistent, high-quality practice. • A deliberate shift toward a more qualified workforce mix, targeting a higher proportion of professionally qualified staff in residence care teams over time.
[5 empty] | Lifting capability through targeted recruitment of frontline staff. | No timeframe has been provided for roll-out of the redesigned Youth Worker recruitment process as this is currently unknown. | Progressing - on track | In 2025, Oranga Tamariki introduced targeted improvements to strengthen staff vetting, screening, and onboarding processes across its secure residences. A redesigned Youth Worker recruitment process, incorporating multiple assessment methods, has been piloted at one residence. Feedback from the pilot has been reviewed and a range of enhancements identified. Rolling out enhancements in recruitment process for all residences is in the planning stage.
[5 empty] | Enhancing leadership and culture in residences with a focus on personal accountability. |  | Progressing - on track | Leadership development, including the culture that is led from the top in residences, is a key aspect of individual action plans for each residence. Residence Mangers are accountable for delivery of their residence action plan. The relevant Manager Residential Care is accountable to the Deputy Chief Executive for delivery of all plans across their span their responsibility. Frontline leadership training has been rolled out to residences, with learning outcomes including being able to explain their roles and responsibilities as a frontline leader. The Professionalising the Residential Workforce Programme includes work on the development of a residence-specific leadership development offering and ongoing professional development optimised for kaimahi training days, which are intended to advance leadership and culture.
[5 empty] | Developing quality assurance of improvement of safety and practice at residences. |  | Progressing - on track | The annual residence review of Care and Protection and Youth Justice residences' compliance with the Oranga Tamariki Residential Care Regulations will be strengthened to reflect the Model of Care for residence and community homes. The Integrated Safe Care Response programme will develop a monitoring and assurance framework for community and remand homes.
OfM | Oranga Tamariki | Earlier intervention and more holistic youth justice initiatives are needed to reduce offending. |  | 2023/24 | Youth offending is being addressed through the Reducing Youth Offending Programme. Continuing to enable communities to support whānau by using early prevention models, such as Fast Track, or Kotahi te Whakaaro. |  | Progressing - on track | The work programme related to reducing youth offending is continuing. In June 2024 the Government announced $30.6m (over 4 years) to continue the Fast Track programme and to expand the cohort to include 14 to 17 year olds in Auckland, Hamilton, Rotorua and Christchurch. | 2026-02-23
Access to Primary Health Services and Dental Care | Oranga Tamariki | Policies and guidance are unclear, resulting in inconsistencies around caregiver responsibilities and health-related information being shared. | Part Two | 2023 | Review practice guidance to reflect the health needs of tamariki and rangatahi. |  | Complete | The Oranga Tamariki Practice Development Team has reviewed its guidance on caregiver responsibilities and sharing health information. Updated guidance has been developed, along with the Practice Note published in 2025.Taken together, the practice note and the updated guidance strengthen clarity while still allowing the necessary flexibility to respond to the unique needs, age, and circumstances of each tamaiti. They also reinforce the expectation that practitioners work in partnership with caregivers — building the plan together and clearly discussing roles, decision making, and what health information will be shared, so everyone understands what is expected and how we will support the child’s wellbeing. | 2026-02-23
[5 empty] | Embed practice guidance through ‘Learning Cycles’ [Cycle Three due in 2024. |  | Complete | Kaimahi were not taken through the guidance as part of Learning Cycle Three. Kaimahi were provided with the associated guidance during LC3, to support them with how to implement the Practice Approach learning. | 2026-02-23
Access to Primary Health Services and Dental Care | Oranga Tamariki | Caregivers are not well supported to ensure that tamariki and rangatahi health needs are met. | Part Two | 2023 | Review guidance (as above) to clarify expectations of staff relating to primary health services and dental care. |  | Complete | Oranga Tamariki advised that as above, this work is now complete. | 2026-02-23
EoCA | Open Home Foundation | There has been improvement in the frequency of foster parent social worker visits, but this is still low. | Part Three | 2023/24, 2024/25 | Regional Managers Practice to work with social workers to ensure visits are recorded. | 2026-06-01 | Progressing - on track | Plans are being developed with Practice Managers and Regional Managers to support services centres where compliance needs to be lifted. | 2026-03-11
[5 empty] | A plan will be created to support Service Centres who have foster parents that they are struggling to engage with. | 2026-06-01 | Progressing - on track | Plans are being developed with Practice Managers and Regional Managers to support services centres where compliance needs to be lifted. | 2026-03-11
EoCA | Open Home Foundation | Less than half of tamariki and rangatahi plans were updated to reflect the required support to meet their transition-related needs. | Part Five | 2023/24 | Create system alerts in Open Home Foundation's administrative database and case management system, OSCAR. | 2026-12-01 | Progressing on track | This is connected to a bigger system upgrade where alerts need to be created in Open Home Foundation's systems for other items. | 2026-03-11
EoCA | Open Home Foundation | More attention is needed on responding to allegations of abuse. | Part Four | 2024/25 | A review will be undertaken on Open Home Foundation's allegations process. | 2026-12-01 | Progressing - on track | Policy is currently being rewritten, a review on current allegation process is underway, training will be delivered to all senior staff members on how to respond to allegations and abuse. | 2026-03-11
| Open Home Foundation | Compliance with requirements to obtain updates about attendance and to engage with the education provider has shown improvement this year but remains well below full compliance. More needs to be done to address these areas of persistently low compliance. | Part Two |  | Training to be updated to ensure Open Home Foundation's Signs of Safety approach is applied to care. | 2026-06-01 | Progressing - on track | Policy is currently being rewritten, a review on current allegation process is underway, training will be delivered to all senior staff members on how to respond to allegations and abuse. | 2026-03-11
EoCA |  |  |  | 2024/25 | Review how Open Home Foundation interacts with educations providers and expectations around this. | On-going | Progressing - on track
EoCA | Open Home Foundation | There is consistently good compliance with health requirements with the exception of dental care. | Part Two | 2024/25 | Create system alert in Open Home Foundation's administrative database and case management system, OSCAR. | 2026-12-01 | Progressing - on track | Open Home Foundation will be creating system alerts in OSCAR to remind social workers to follow up on dental checks. | 2026-03-11
[5 empty] | Work with Foster Parents to ensure they are planning dental visits | On-going | Progressing - on track
EoCA | Open Home Foundation | Some required information is consistently not provided to tamariki and rangatahi when they enter care, including about their rights to give feedback and to make a complaint and about advocacy services that are available to them. | Part Four | 2024/25 | All Tamariki to be given a copy of "My Rights" and have casenoted that there has been a conversation regarding how to make a complaint. | 2026-06-01 | Progressing - on track |  | 2026-03-11
EoCA | Barnardos | When staff lack cultural competence, relationships between Oranga Tamariki, whānau and other organisations can be negatively impacted. | Overarching | 2021/22 | Strengthen connections with local iwi to enable whanaungatanga with the foster care team and caregivers. | Ongoing | Progressing - on track | Barnardos is building its own Māori cultural competence including supporting our various leaders across the motu to build and/or strengthen strategic iwi relationships. Barnardos has an internal Māori development programme named Tīrama that is led by Barnardos’ Kaihautu that is currently being rolled out. | 2026-03-11
EoCA | Ministry of Education | Collaboration and information sharing between government agencies remains a barrier. | Part Two | 2023/24, 2024/25 | Over the next 12 months the Ministry and Oranga Tamariki will identify further data to share that will support attendance, engagement and achievement at school (5/09/2025). | Initial data share complete. Monthly data shares are on-going. | Progressing - on track | Completed the first detailed data schedule for sharing with Oranga Tamariki on attendance and enrolment (November 2025), inclusive of on-going monthly data shares. Continuing to refine the data share on Attendance and Engagement (February 2026 - on-going). | 2026-02-26
[5 empty] | Establish an Information Sharing Agreement (ISA) with Oranga Tamariki, supporting regular sharing of enrolment and attendance data. |  | Complete
[5 empty] | Communicating and embedding escalation pathways between Oranga Tamariki and Ministry of Education at local, regional, and national levels | 2027-06-01 | Progressing - on track
[5 empty] | Improve data quality in collaboration with Oranga Tamariki | 2027-06-01 | Progressing - on track
[5 empty] | Complete a stocktake of regional information sharing arrangements and co-develop regional actions with Oranga Tamariki for the Oranga Tamariki System Action Plan. | 2027-06-01 | Progressing - on track
EoCA | Ministry of Education | Tamariki and rangatahi are not always getting the support they need for education. | Part Two | 2023/24, 2024/25 | We have identified changes we can make to help address this issue: improvements to our operational guidance for directed enrolments; information about these processes for schools and our Oranga Tamariki colleagues. We will incorporate these improvements into our Attendance Action Plan. | 2026-09-01 | Progressing - on track | This work is being progressed as part of the Attendance Work Programme as an identified barrier. The development of operational policy is pending while we address resourcing challenges. | 2026-02-26
[5 empty] | The Gateway Assessment review identified improvements that could be made to the education profile to better inform Gateway Assessments. We have created an improved profile and are currently testing this with colleagues at the Ministry of Health and Oranga Tamariki to ensure the changes will support the assessment process. We are considering process improvements that will increase timeliness and accountability. |  | Complete | Three education profiles (Primary & Secondary, Early childhood education (ECE), and Non-enrolled) and supporting guidance have been reviewed, approved, and shared with Oranga Tamariki for upload into CYRAS. | 2026-02-26
[5 empty] | Attendance Action Plan to incorporate improvements to operational guidance for directed enrolments and share information about these processes for schools and Oranga Tamariki kaimahi. | 2026-06-30 | Progressing - on track
[5 empty] | Develop guidance to enable Ministry and Oranga Tamariki staff and caregivers to work collaboratively to enrol and support tamariki and rangatahi in education. This would include: - escalation pathways - directed enrolments - supports available and how to access them | 2026-12-01 | Progressing - on track
[5 empty] | Co-develop and deliver a professional learning package with Oranga Tamariki to implement guidance | 2027-06-01 | Progressing - on track
EoCA | Ministry of Health | Gateway assessments continued to be valued, but there are barriers to getting them. | Part Two | 2023/24, 2024/25 | Health New Zealand and Oranga Tamariki are progressing national improvements to the current Gateway service to enable improved access to health, education, and disability services. These changes include improvements to contract settings, consent processes and clearer processes and pathways. | End 2027 | Progressing - on track | Health New Zealand and Oranga Tamariki have been working to scope and plan for the implementation of national improvements to the current Gateway service to enable earlier access to health, education and disability services. A phased approach to progressing the improvements is being planned. The minor risk status is due to delays in finalising a high-level implementation plan and resourcing constraints. | 2025-08-29
EoCA | Ministry of Health | Access to mental health services is particularly challenging for children in care. | Part Two | 2023/24, 2024/25 | Training will be provided to Oranga Tamariki social workers to increase capability and better support children with mental health and addiction needs and improvements for group homes and residences. | End 2027 | Progressing - on track
[5 empty] | Oranga Tamariki and Health New Zealand have been considering how to improve interagency collaboration at service level and have established new liaison roles in both Oranga Tamariki and Health New Zealand settings. | End 2027 | Progressing - on track
[5 empty] | Health New Zealand has contracted training for mental health services to support working with Oranga Tamariki. Health New Zealand is working with Oranga Tamariki to provide training on mental health for Oranga Tamariki frontline workers. | End 2027 | Progressing - on track
EoCA | Ministry of Health | There is a lack of assurance that health needs are being met. Tamariki and rangatahi are not all having an annual health check as required by the NCS Regulations. It is not clear what an annual health check should include. | Part Two | 2023/24, 2024/25 | Make the care status of children in the care of Oranga Tamariki visible within the health system (working in conjunction with Health New Zealand and Oranga Tamariki). | End 2027 (but was originally planned for end of 2026) | Progressing - off track | In December 2025, Ministers agreed to the proposed settings to ensure children in care are visible within the health system. A project plan is currently being developed by agencies. | 2026-02-27
[5 empty] | Guidance for health practitioners will be developed to support them to tailor their practice and respond to the unique needs of children and young people in care (working in conjunction with Health New Zealand and Oranga Tamariki). | End 2027 (but was originally planned for end of 2026) | Progressing - off track | Guidance for health workers is being planned as part of the above action to make children in care visible in the health system. | 2025-08-29
[5 empty] | The Ministry of Health and Health New Zealand will be involved in the work Oranga Tamariki has underway to look at what an annual health check could involve. | No completion data specified (as Oranga Tamariki is leading this work). | Progressing - on track | Ministry of Health and Health New Zealand last met with Oranga Tamariki in November 2025. Work is ongoing between agencies. Oranga Tamariki is leading this work. | 2026-03-10
[5 empty] | Be involved in the interagency work with Oranga Tamariki to develop a two-way information sharing agreement to support health practitioners to be more responsive to the needs of children in care and support improved monitoring of health engagement and frequency. | End 2027 | Progressing - on track | Health New Zealand has advised that activity is progressing, including regular engagement with Oranga Tamariki, early scoping of data‑sharing needs, and initiation of the Privacy Impact Assessment process. Health New Zealand has established a project team and completed internal planning, timelines, and resourcing preparations. | 2026-03-11
Note on F100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Provided the same response for a separate finding
Note on F102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Provided as a planned action for EoCA above
Note on F105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Provided as a planned action for EoCA above

## Don't delete
Part One
Part Two
Part Three
Part Four
Part Five
Part Six
Overarching